## Risk-assessement
RISK ID | Risk Category | Risk Description | Risk Level | Risk Management Strategy
RID01 | Regulatory Compliance | Not Implementing proper security measures | High | Making sure that through compliance assessment is conducted before migrating the network to cloud.
RID02 | Regulatory Compliance | Compliance followed by vendor | Medium | Selecting the cloud service provider with requires Compliance certificate.
RID03 | Regulatory Compliance | Not having control over the data | High | Making sure that as a company we conduct regular audits and making sure cloud provier follows the laws and regulations.
RID04 | Security Risk | Encrypted Data | High | Making sure all the data the is being stored in cloud in encrypted
RID05 | Security Risk | Access Management | High | Making sure only specific access is granted to employees/ contractors and revoked when not needed. Stale accounts should be deleted.
RID06 | Security Risk | Data Loss | medium | Migrating servers to cloud could lead to data corruption or loss. Making sure required backups are taken before migrating the VM.
RID07 | Cost | Running both environment | Medium | Making sure that the migration is planned in best way and on premise resources are shut after migration.
RID08 | Cost | Resource allocation | High | Making sure that only requied resources are allocated to the VM or network. Inefficient allocation of resources could lead to increase operational cost. Making sure that required tools are used to keep track of the cost.
RID09 | operational | Downtime during Migration | Low | Minimising the downtiem during migraton. Making sure that business is informed and migration is planned accordingly.
RID10 | operational | Compatibility issues | Hight | Making sure that appliatons and services that are being used in on-premise network are availale and compatible in on premise network.
ref:https://learn.microsoft.com/en-us/azure/cloud-adoption-framework/govern/assess-cloud-risks#example-risk-list